## Gantt Chart
Project Title |  | Predicting the Popularity of Rental Listings in San Francisco
Class |  | CIS 5570 Big Data | [60 empty] | 2025-02-03
Student Names |  | Salem Sharak | Ilyas Ahmed | Omar ElHaik
Task Number | Task Title | Start Date | Due Date | Completion Date | Duration | % Complete | March | [27 empty] | April
[7 empty] | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8
[7 empty] | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
 | time axis 2020-03-02 to 2020-04-26
1 | Project Initiation and Data Collection |  |  |  |  | 80%
1.1 | Selection of Data Set and Checkpoint 1 | 2020-03-02 | 2020-03-02 | 2020-03-02 | 1 | 100%
1.2 | Choose relevant attributes and prepare cleaned sample copy of data | 2020-03-20 | 2020-03-28 | 2020-03-25 | 6 | 100%
1.3 | Determine attribute (mix) used to predict the popularity of a listing | 2020-03-20 | 2020-03-28 |  | 9 | 50%
1.4 | (opt.) Look into solved examples online | 2020-03-18 | 2020-03-26 |  | 9 | 50%
1.5 | Prepare the complete cleaned dataset | 2020-03-18 | 2020-04-03 | 2020-03-25 | 8 | 100%
2 | Algorithm Selection |  |  |  |  | 0%
2.1 | Look into relevant algorithms online/literature | 2020-03-23 | 2020-03-29 |  | 7 | 0%
2.2 | Come up with idea of how to implement in code (locality sensitive hashing?) | 2020-03-26 | 2020-03-29 |  | 4 | 0%
2.3 | Write document comparing algorithms and select best ones | 2020-03-27 | 2020-03-31 |  | 5 | 0%
3 | Application of Algorithm(s) (Evaluation) |  |  |  |  | 0%
3.1 | Set up Spark environment | 2020-03-31 | 2020-04-01 |  | 2 | 0%
3.2 | Write programs to apply the selected algorithms | 2020-04-01 | 2020-04-09 |  | 9 | 0%
3.3 | Compare results of different algorithms - Accuracy, Prec., Recall, F1 | 2020-04-09 | 2020-04-12 |  | 4 | 0%
4 | Results and Report Writing |  |  |  |  | 0%
4.1 | Write draft outline of report | 2020-04-05 | 2020-04-08 |  | 4 | 0%
4.2 | Select key datapoints to visualize | 2020-04-07 | 2020-04-11 |  | 5 | 0%
4.3 | Generate graphs | 2020-04-11 | 2020-04-13 |  | 3 | 0%
4.4 | Break down sections and fill in with results | 2020-04-08 | 2020-04-17 |  | 10 | 0%
0 | Additional Tasks With No Set Date
0.1 | One Cool Thing | 2020-03-27 | 2020-03-31 |  | 5
0.2 | Exam 2 | 2020-04-07 | 2020-04-07 |  | 1
0

## Literature Review
Literature Review Articles
Tier 1
Download PDF | It's Got the Look: The Effect of Friendly and Aggressive "Facial" Expressions on Product Liking and Sales
Download PDF | The Beauty of Simplicity
Download PDF | Colour appeal in website design within and across cultures: A multi-method evaluation
Download PDF | Check Out This Place: Inferring Ambiance From Airbnb Photos
Download PDF | A computational framework for understanding antecedents of guests' perceived trust towards hosts on Airbnb
Download PDF | Neighborhood and Price Prediction for San Francisco AirbnbListings
Tier 2
Download PDF | Feeling a destination through the “right” photos: A machine learning model for DMOs’ photo selection
Download PDF | Measuring the gap between projected and perceived destination images of Catalonia using compositional analysis
Download PDF | To buy or not to buy: Influence of seller photos and reputationon buyer trust and purchase behavior
Download PDF | Commercial use of conjoint analysis in Europe: Results and critical reflections
Download PDF | Exploring Human Images in Website Design: A Multi-Method Approach
Download PDF | The Role of Color Contrast and Predominant Primary Color of Icons for Mobile Gaming Apps in Influencing User Reactions
Download PDF | The impact of human brand image appeal on visual attention and purchase intentions at an e-commerce website
Download PDF | Visual attention to the main image of a hotel website based on its position, type of navigation and belonging to Millennial generation: An eye tracking study
Download PDF | Download Appendix | Predicting the Personal Appeal of Marketing Images Using Computational Methods
Download PDF | Using image-based and text-based information for sales prediction: A deep neural network model